## Pre-filled Starter Sheet (2)
Purpose Conveys the scope of various tasks that need to be coordinated to build and launch the product/feature | What is the task? Based on the purpose, select the appropriate from the drop-down | Who is the task owner? Does the following to finish task: 1. Schedule and run meetings 2. Gather feedback and share updates 3. Follow-up with stakeholders | Whose involvement is needed to accomplish the task ? Please select one from the drop-down list of your identified stakeholders | What is their role? Select the stakeholder's role from the drop-down. Note: 'Scrum Team' role is applicable to stakeholder 'Scrum Team' only | By when, does the task need to be completed? Select milestone keeping in mind nature of the task,downstream effects of delaying task
Evangelize internally | Setup PRD review meeting to receive feedback | Product Manager | Head of Product | Approvals | On going activity
|  |  | Cross-functional Stakeholders | Feeback
| Creating bi-weekly newsletters and competitive battle cards |  | Engineering | Contributors (Consulted for their opinions or expertise to help with project decisions)
| Setup meeting to kickoff project with the scrum team |  | Scrum Team | Scrum Team (Involved directly in product development efforts)
Involve legal and compliance | Legal compliance | Product Manager | Legal, Leadership, Engineering, Marketing. Sales | Legal , Finance team, Management | After 4 sprints,involve legal early in the product development, to check for all the compliance and the 3rd part support and open software to be incorporated,so that we are not sued for the breach
| Open source inclusion |  | Seek legal opinion on MPL/GPL/LGPL licensese | Make sure that we are all on the same page on the product notes ,produt releases and publicl announce any open source software included in the product . | Ongoing activity
Incorporate stakeholders feedback | Get feedaback from all the internal stakeholds | Product Manager | Product Designer, Development,Management, QA | Scrum Team (Involved directly in product development efforts) | Ongoing activity
Initiate and maintain feedback loop | Provide feedback on the features /solution as a whole | Product Manager | Head of Product/Impacted Product Managers/Cross-functional stakeholders |  | Ongoing activity
Plan development work | Enable the login feature both on ioS and Android platform | Engineering Lead | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before project's sprint 0 starts
| Enable the payment gateway by integrating the payment gateway API | Engineering Lead
Manage product/feature testing | Share and review the project's test strategy | QA | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before each sprint starts
Setup analytics tracking | Create a project-specific communication channel (in Slack etc) to share insights from customer meetings/usability tests/data analysis | Data Analyst | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before each sprint ends
Prepare for every sprint | Updates | Product Manager | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before each sprint starts
| Create tickets for each sprint based on the analytics tracking requirements | Data Analyst
| Create burn down charts | Product Manager
Coordinate product/feature launch | Marketing collaterals | Product Marketing | Product Manager | Product marketing | Ongoing activity
| Organizing the | Product Marketing | Product Manager | Plan for the launch and press releases | Before project's last sprint ends
Communicate project progress | Weekly mailer and bi-weekly newsletter | Product Manager | All except Legal and Compliance | Cadence call with the internal stakeholders and bi-weekly mail to the entire organization on the progress | Ongoing activity
Receive product/feature sign-off | Setup meeting to demo the feature and conduct end-to-end feature testing to identify bugs and receive feedback | Product Manager | Head of Product/Impacted Product Managers/Cross-functional stakeholders | Feeback | Ongoing activity
|  |  | Impacted Product Managers | Provide feedback on timely basis

## Help Information
Stakeholders identified for the project
Head of Product
Impacted Product Managers (Your product/feature impact the product/feature they mange directly or indirectly)
Cross-functional Stakeholders (Representation from these areas: Customer Service, Marketing (includes Product Marketing) and Operations )
Scrum Team (Mentioned here)
Legal and Compliance
Customer Service